## Summary
JDA 1 Overall Progress (TEST DATA)
Report date | 2026-09-28
Overall status | Amber (at risk)
Reason | Well Log Quality Assistant is behind plan

## Projects
Project | Owner | % Complete | Status | Description
Seismic Data Lake | IBM Malaysia | 72 | Green | Ingestion and cataloguing of legacy seismic surveys.
Well Log Quality Assistant | Tridiagonal.ai | 45 | Amber | Automated completeness and unit checks for well logs.
Reservoir Study Copilot | IBM Malaysia | 30 | Green | Search and drafting assistant for reservoir studies.
Production History Matching | Tridiagonal.ai | 15 | Red | ML-assisted history matching for 4 pilot fields.

## Challenges
Severity | Challenge | Description | Mitigation
High | Legacy tape formats | About 8% of surveys are on tape formats that need a third-party reader. | Vendor engaged; transcription to start in October.
Medium | Log mnemonic inconsistency | Curve names differ between fields and vintages. | Shared mnemonic dictionary agreed with asset teams.
Low | Pilot field data access | Two pilot fields need additional access approval. | Approval request submitted; expected within two weeks.

## S-Curve
Month | Planned % | Actual %
Jul 2026 | 10 | 8
Aug 2026 | 22 | 20
Sep 2026 | 36 | 33
Oct 2026 | 50
Nov 2026 | 64
Dec 2026 | 76
Jan 2027 | 88
Feb 2027 | 100